## Project Dashboard
SmartCatalog: E-Commerce Discovery Engine
Spring Boot 3.3.x ¦ Java 21 ¦ pgvector ¦ Redis
Project Tracking
Total Tickets
To Do
In Progress
Done

## Backlog
Issue Key | Type | Epic | Summary | Status | Priority | Sprint | Story Points | Tech & Libraries | User Story & Use Case | Implementation Guide
SC-1 | Task | Infrastructure | Initialize Spring Boot App | To Do | High | Sprint 1 | 2 | Spring Boot 3.3.x, Java 21, Web, Data JPA | As a developer, I need a baseline Spring Boot project so I can begin building the REST APIs. Use Case: Foundation setup. | 1. Go to start.spring.io 2. Select Maven, Java 21, Spring Boot 3.3.x. 3. Add dependencies: Spring Web, Spring Data JPA, PostgreSQL Driver, Lombok, Validation. 4. Enable Virtual Threads in application.yml: `spring.threads.virtual.enabled=true`.
SC-2 | Task | Infrastructure | Setup Local Infrastructure via Docker | To Do | High | Sprint 1 | 3 | Docker Compose, pgvector:pg16, Redis 7.2 | As a developer, I need local instances of my databases so I can run the app without external dependencies. Use Case: Local environment provisioning. | 1. Create `docker-compose.yml` in root. 2. Define a service for `pgvector/pgvector:pg16` mapping port 5432. 3. Define a service for `redis:7.2-alpine` mapping port 6379. 4. Add healthchecks to ensure DBs are ready before app starts.
SC-3 | Story | Security | Implement Stateless JWT Authentication | To Do | High | Sprint 1 | 5 | Spring Security, jjwt | As an API consumer, I need to authenticate securely via tokens so my data is protected. Use Case: Login and secure API access. | 1. Create `JwtUtil` class for generating/validating tokens. 2. Create `JwtAuthenticationFilter` extending `OncePerRequestFilter` to extract Bearer tokens. 3. Configure `SecurityFilterChain` to permit /auth endpoints and require authentication for others.
SC-4 | Task | Security | Global Exception Handling (RFC 7807) | To Do | Medium | Sprint 1 | 3 | Spring ProblemDetail | As a frontend/mobile client, I need structured error responses so I can parse validation errors easily. Use Case: Standardizing 400/500 HTTP responses. | 1. Create `GlobalExceptionHandler` annotated with `@RestControllerAdvice`. 2. Create handlers for `MethodArgumentNotValidException` and custom domain exceptions. 3. Return `ProblemDetail.forStatusAndDetail()` to comply with RFC 7807.
SC-5 | Task | Database | Configure Flyway Database Migrations | To Do | High | Sprint 2 | 3 | Flyway-core | As a developer, I need schema version control so database changes are reproducible across environments. Use Case: Safe table creation. | 1. Add Flyway dependency. 2. Create `src/main/resources/db/migration/V1__init_schema.sql`. 3. Write CREATE TABLE statements for users, products, categories. 4. Include `CREATE EXTENSION IF NOT EXISTS vector;`.
SC-6 | Story | Database | Design JPA Entities & Auditing | To Do | High | Sprint 2 | 5 | Spring Data JPA | As a system, I need object mappings for my database so I can interact with records using Java objects. Use Case: Data persistence. | 1. Create `Product`, `Category` entities. 2. Add `@Entity`, `@Table`. 3. Implement `@CreatedDate` and `@LastModifiedDate` using `@EntityListeners(AuditingEntityListener.class)`. 4. Add `@Version` for optimistic locking.
SC-7 | Story | API Core | Build CRUD REST APIs for Catalog | To Do | High | Sprint 2 | 5 | Spring MVC, MapStruct | As an admin, I need to create and read products so I can manage the e-commerce catalog. Use Case: Basic inventory management. | 1. Create `ProductController` with standard GET, POST, PUT. 2. Use MapStruct to map `Product` entity to `ProductDto`. 3. Implement pagination via `Pageable` in the repository. 4. Use `@EntityGraph` to avoid N+1 queries when fetching categories.
SC-8 | Story | Performance | Integrate Redis Caching for Reads | To Do | High | Sprint 3 | 3 | Spring Data Redis, @Cacheable | As a user, I need fast response times for popular products so the app feels snappy. Use Case: Reducing DB load. | 1. Add `@EnableCaching` to main class. 2. Configure `RedisCacheManager` with a 1-hour TTL. 3. Add `@Cacheable(value = "products")` to the GET products endpoint. 4. Add `@CacheEvict` on POST/PUT endpoints to clear stale data.
SC-9 | Story | Performance | Implement Rate Limiting on Search API | To Do | Medium | Sprint 3 | 3 | Bucket4j | As a platform owner, I need to protect my search API from bots so I don't incur high AI/DB costs. Use Case: API abuse prevention. | 1. Integrate Bucket4j. 2. Create a Filter or Interceptor to check remaining tokens based on IP or User ID. 3. Configure a bucket to allow 20 requests per minute. 4. Return HTTP 429 Too Many Requests if bucket is empty.
SC-10 | Task | AI Search | Configure Spring AI & Credentials | To Do | High | Sprint 4 | 2 | Spring AI OpenAI | As a system, I need to connect to an LLM provider so I can generate embeddings for products. Use Case: AI integration setup. | 1. Add `spring-ai-openai-spring-boot-starter`. 2. Add `spring.ai.openai.api-key` to application.yml (read from environment variable). 3. Inject `EmbeddingModel` into a test service to verify connectivity.
SC-11 | Story | AI Search | Auto-Generate Embeddings on Product Save | To Do | High | Sprint 4 | 5 | Spring AI EmbeddingModel | As an admin, when I create a product, I need it to be searchable semantically without manual work. Use Case: Vectorizing inventory. | 1. Create a `ProductObserver` or use JPA `@PostPersist`/`@PostUpdate`. 2. Combine product title, category, and description into a single string. 3. Call `embeddingModel.embed(text)`. 4. Save the resulting `List<Double>` to the product's vector column.
SC-12 | Epic | AI Search | Build Hybrid Search API (Vector + SQL) | To Do | Highest | Sprint 4 | 8 | pgvector, native queries | As a user, I need to search by intent (e.g., 'warm jacket') and price filters simultaneously. Use Case: Semantic E-commerce Search. | 1. Create a GET /search endpoint taking a `query` string and `maxPrice`. 2. Convert user `query` into an embedding vector. 3. Write a Spring Data `@Query(nativeQuery=true)` that uses `embedding <=> cast(:vector as vector)` to sort by similarity while filtering by price. 4. Return the top 10 mapped DTOs.
SC-13 | Task | Testing | Configure Testcontainers for Integration Tests | To Do | High | Sprint 5 | 3 | Testcontainers PostgreSQL | As a developer, I need to run my integration tests against real databases so I catch pgvector syntax issues. Use Case: CI/CD test reliability. | 1. Add testcontainers dependencies. 2. Create a `@SpringBootTest` base class. 3. Define a `@ServiceConnection` for `PostgreSQLContainer` (using pgvector image) and `GenericContainer` (for Redis). 4. Ensure context boots successfully.
SC-14 | Story | Testing | Write E2E Integration Test for Hybrid Search | To Do | High | Sprint 5 | 5 | JUnit 5, MockMvc | As a developer, I need to verify that a semantic search query accurately ranks the right database records. Use Case: Verifying AI search logic. | 1. Write a test that inserts 3 distinct products (e.g., Winter Coat, Summer T-Shirt, Coffee Mug). 2. Call the search API with 'snow clothing'. 3. Assert that 'Winter Coat' is returned as the first result using JSONPath. 4. Assert HTTP 200.